## Timetable
Days from zero | Time from zero | Time-limit | Activity | Responsible
-365 | - 1 year | -365 | Signed contract | ECVD and Organiser
-240 | - 8 months | -240 | Invitation to member countries | ECVD General Secretary
-210 | - 7 months | -210 | Return of provisional entry sheets | Member nations
-210 | - 7 months | -210 | Copy of entry forms to organiser and TO | ECVD General Secretary
-180 | - 6 months | -180 | Nomination of the participating teams | ECVD Technical Officer
-180 | - 6 months | -180 | Nomination list to the nominated teams. | ECVD General Secretary
-180 | - 6 months | -180 | Invoice Registration Fee, Referee Fee, XX €, to nominated teams | ECVD General Secretary
-180 | - 6 months | -180 | Final entry forms to nominated teams | ECVD General Secretary
-90 | - 3 months | -90 | Competition regulations | ECVD Technical Officer
-90 | - 3 months | -90 | Inspection of venue, accommodation, and meeting with local organiser | ECVD Technical Officer
-90 | - 3 months | -90 | Drawing of pools | ECVD Technical Officer
-56 | - 8 weeks | -56 | 1st bulletin to all nominated teams with registration forms and information according to the competition manual. | Organiser
-56 | - 8 weeks | -56 | Nomination of one/two classifiers | WOVD medical commission
-56 | - 8 weeks | -56 | Nomination of referees | ERC
-56 | - 8 weeks | -56 | Playing schedule. | ECVD Technical Officer
-56 | - 8 weeks | -56 | Nomination of ECVD officials | ECVD Technical Officer
-49 | - 7 weeks | -49 | Answers and forms from referees | Nominated referees
-42 | - 6 weeks | -42 | Answer from the teams with the team registration forms. | Nominated teams
-42 | - 6 weeks | -42 | List of nominated referees with addresses to ECVD General Secretary | ERC
-42 | - 6 weeks | -42 | Name and address of clasifier to ECVD General Secretary | WOVD medical commission
-42 | - 6 weeks | -42 | List of nominated officers with addresses to ECVD General Secretary | ECVD Technical Officer
-35 | - 5 weeks | -35 | List of nominated officials with addresses to organiser | ECVD General Secretary
-28 | - 4 weeks | -28 | Invoice participation fees and security fee to nominated teams | Organiser
-28 | - 4 weeks | -28 | 1st bulletin to all nominated officials. | Organiser
-28 | - 4 weeks | -28 | Match schedule | Organiser
-28 | - 4 weeks | -28 | List of participating teams and players to ECVD Technical officer and WOVD Classifier | Organiser
0 | Zero |  | Latest arrival of ECVD officials | ECVD Technical Officer
1 | + 1 day | 1899-12-31 | Competition meeting (organiser + officials) | Technical Delegate
1 | + 1 day | 1899-12-31 | Arrival of ECVD board | Organiser
1 | + 1 day | 1899-12-31 | Arrival of referees | Organiser
1 | + 1 day | 1899-12-31 | Latest arrival of teams – Training – Classification | Organiser
2 | + 2 days | 1900-01-01 | Training – Classification | Organiser
2 | + 2 days | 1900-01-01 | Technical meeting | Organiser/Technical Delegate
3 | + 3 days | 1900-01-02 | Competition | Organiser
4 | + 4 days | 1900-01-03 | Competition | Organiser
5 | + 5 days | 1900-01-04 | Competition | Organiser
6 | + 6 days | 1900-01-05 | Competition (European Championship) | Organiser
6 | + 6 days | 1900-01-05 | Departure (Euro Cup) | Organiser
7 | + 7 days | 1900-01-06 | Departure (European Championship) | Organiser
Formulas:
Time-limit = +C28+[Days from zero]